## Sheet1
CHANGE ORDER No. |  | 1 |  |  | 2018-08-01
Project: | Audio Visual and Campus Communication Systems
Bid No.: | RFP#17-18/003
DSA No:
The following parties agree to the terms of this Change Order:
Owner: Beverly Hills Unified School District Contractor: Digital Networks Group(name)
255 South Lasky Drive 20382 Hermana Circle
Beverly Hills, California 90212 Lake Forest, CA 92630
This Change Order is subject to approval by the School Board and must be signed by the District, and the Contractor.
Contract Date: |  |  | 2017-10-24
Original Contract Amount: |  |  | 1314867 |  | The Contract time will be changed by 0 days. The date of Substantial Completion as of the date of this change order is 8/03/18.
The Contract Sum Prior to this change order was: |  |  | 1314867
The Contract Sum was changed by this Change order in the amount of: |  |  | -310696.36
The new Contract Sum including this change order wiII be: |  |  | 1004170.64
The Contract time is NOT changed: |  |  | 0 | days.
The contract Substantial Completion date effective this CO is: |  |  | 2018-08-03
SIGNATURES
Owner: |  |  |  | Contractor:
Beverly Hills Unified School District |  | Date |  | Name | Date
RECOMMENDED FOR APPROVAL |  |  |  | Description:
Construction Manager |  |  |  | This change order is a reduction of cost based on
Director Of Construction |  |  |  | value engineering performed by District IT and IT
Program Manager |  |  |  | consultants for the AV equipment installed in Horace
IOR |  |  |  | Mann Building A
Architect
All Items included in this Change Order are summarized on the following pages. Copies of the Contractor's proposal and cost break down of each item are attached.
Note:
Contractor agrees to furnish all labor and materials and perform all of the described work in accordance with the terms below in compliance with the applicable section of the Contract Documents. The amount of the charges under this Change Order is limited to the charges allowed under Article 49 of the General Conditions. The adjustment in the contract sum, if any, and the adjustment in the contract time, if any, set out in this Change Order shall constitute the entire compensation and/or adjustment in the contract time and contract sum due to the Contractor arising out of the change in the work covered by this Change Order, unless otherwise provided in this Change Order. It is understood that this Change Order shall be effective when approved by the governing Board of the District.
Beverly Hills Unified School District
Measure E Bond Program